## SC Working Plan 2021-2023
Year | Project code | Lead | Summary Title | Provider | Report author | Date ToR published | Consultant Recruitement | Draft report submission date | Date final report due | WG/SC meeting | Funding (Euro) | Funding source | Project Status | Requirement reference | Pre-requisite projects | Meeting paper reference | Comments
2020/21 | SER2019-01 | SERAWG | ALF ageing | Consultant | Fish Ageing Services Pty Ltd (Krusic-Golub and Robertson) | xx-09-2019 | 18-10-2019 | 30 April 2020 | 2020-06-01 | SERAWG4 | 16000 |  | Completed |  |  | SERAWG-04-INFO-01 | Report submitted as info paper to SERAWG4
2020/21 | PAE2020-01 | PAEWG | BFIA trawl & longline | Consultant | SoFish Consulting (Mormede) | 2020-10-05 | 2020-11-05 | 2021-01-31 | 2021-06-01 | PAEWG4 | 57870 | MoP; Australia | Completed | MoP5 |  | PAEWG-03-08 (interim) PAEWG-04-05 (final) | Final report submitted as working paper to SERAWG4
2020/21 | SER2020-01 | SERAWG | Harvest strategies | Consultant | CT university (Butterworth) | 2020-11-25 | 2020-12-11 | 2021-02-04 | 2021-03-01 | SERAWG3 | 15000 | MoP6 | Completed | MoP6 |  | SERAWG-03-10
2020/21 | PAE2020-02a | PAEWG | VME mapping (year 1) | Consultant | BOREA Laboratory (2020-2021) | Completed | Completed | 2021-01-30 | 2021-03-01 | PAEWG3 | - | MoP | Completed | MoP5 |  | PAEWG-03-06 | report was submitted to PAEWG3
2020/21 | - | PAEWG | VME indicator species | Secretariat | SIOFA Secretariat (2021) | N/A | N/A | - | 2021-03-01 | PAEWG3 | - | MoP | Completed | SC5 Annex I |  | PAEWG-03-07 | report was submitted to PAEWG3
2020/21 | - | PAEWG | SIOFA Fishing Footprint | Secretariat | Secretariat (2021) | N/A | N/A | - | 2021-01-01 | SC6 | - | MoP | Completed | MoP5 |  | SC-06-28
2020/21 | SCM2021-01 | SC/SEC | Science Manager for EU projects | Consultant | Gary Morgan | 2021-01-15 | 2021-02-10 | 2022-01-19 | 2022-02-19 | SC7; SC8 | 15000 | EU Grant (GO5) | Ongoing | EUG 2020 GO5 |  |  | Interim report to be delivered to SC7
2021/21 | SER2021-01 | SERAWG | ORY collation of additional acoustic data (ToR 1) | Consultant | Aqualyd (Macaulay) | 2021-04-30 | 2021-05-24 | 2021-12-29 | 2022-01-29 | SERAWG4 | 3800 | MoP7 | Completed | SC6 Annex G |  | SERAWG-04-05 | Final report to be presented to SERAWG4 (final payment to be done after validation by Chair)
2021/21 | SER2021-01 | SERAWG | ORY acoustic data quality control (ToR 2) | Consultant | Aqualyd (Macaulay) | 2021-04-30 | 2021-05-24 | 2021-12-29 | 2022-01-29 | SERAWG4 | 8550 | MoP7 | Completed | SC6 Annex G |  | SERAWG-04-06 | Final report to be presented to SERAWG4 (final payment to be done after validation by Chair)
2021/21 | SER2021-01 | SERAWG | ORY acoustic biomass estimation (ToR 3) | Consultant | Aqualyd (Macaulay) | 2021-04-30 | 2021-05-24 | 2021-12-29 | 2022-01-29 | SERAWG4 | 6650 | MoP7 | Completed | SC6 Annex G |  | SERAWG-04-07 | Final report to be presented to SERAWG4 (final payment to be done after validation by Chair)
2021/22 | SER2021-02 | SERAWG | ORY ageing + growth | Consultant | NIWA (Saunders) | 2021-06-29 | 2021-07-16 | 2021-10-15 | 2022-01-29 | SERAWG4 | 10000 | EU Grant (GO1.3) | Completed | SC6 Annex G | SER2021-01 | SERAWG-04-08 | Final report to be presented to SERAWG4 (final payment to be done after validation by Chair)
2021/22 | SEC2021-10 | SC/SEC | SIOFA Science Officer Recruitment | Secretariat |  | 2021-08-15 | 2021-10-15 | N/A | N/A | N/A | - | MoP8 | Completed | MoP8 para 192 |  | SIOFA circular 2021-42 | In place on 1st February 2022
2021/22 | SER2021-03 | SERAWG | Saya de Maya Bank Scoping Study | Consultant | MRAG (Temple) | 2021-08-15 | 2021-09-15 | 2021-12-29 | 2022-01-29 | SERAWG4 | 15000 | EU Grant (G01.4) | Completed | MoP8 para 145 |  | SERAWG-04-10 | Initialy scheduled for SC8, but was brought forward to SC7 by MoP8. Final report submitted to SERAWG4 as restricted document
2021/22 | PAE2021-02 | PAEWG | Seabirds & mammals ERAEF (PAE202102-ToR1) | Consultant | Ross Analytics (Keith Reid) | 2021-10-25 | 01-10-2021 | 2022-01-05 | 2022-02-05 | PAEWG4 | 10000 | EU Grant (GO3) | Completed | SC6 Annex G |  | PAEWG-04-06 | report submitted to PAEWG4 (late)
2021/22 | PAE2021-04 | PAEWG | SIOFA Fishing Footprint (update) | Secretariat | Secretariat | N/A | N/A | 2022-01-19 | 2022-02-19 | PAEWG/SC7 | - | - | Completed | MoP8 para 110 | PAE2020-01 | PAEWG-04-12
2021/22 | SEC2021-03 | SC/SEC | Joint SIOFA-CCAMLR SC meeting of toothfish data exchange | SC Chairs committee |  | N/A | N/A | N/A | 2022-02-05 | SC7 | - | - | Completed | MoP8 para 201-203; SC6 para 156 |  | SERAWG-04-INFO-04 | report of the meeting submitted to SERAWG4
2021/22 | SEC2021-07 | SC/SEC | Fisheries summaries | Secretariat |  | N/A | N/A | 2022-01-19 | 2022-02-19 | SERAWG4/SC7 | - | - | Completed | MoP8 para 115; SC6 para 142-146 |  | SERAWG-04-18 | submitted to SERAWG4 as a restricted paper
2021/22 | SEC2021-08 | SC/SEC | Toothfish tagging programme | Secretariat |  | N/A | N/A | 2021-12-29 | 2022-01-29 | SERAWG4 | - | - | Completed | MoP8 para 97 |  | SERAWG-04-16 | submitted to SERAWG4
2021/22 | - | SERAWG | Monitoring, Management and Impact Mitigation in the shark bycatch | SC Delegations | EU delegation | N/A | N/A | 2021-12-29 | 2022-01-29 | SERAWG4 | - | - | Completed | CC6 para 17 |  | SERAWG-04-13 | submitted to SERAWG4 by the EU delegation
2021/22 | SER2021-07 | SERAWG | ERA Teleosts | SC Delegations | Australia | N/A | N/A | N/A | 2023-01-31 | SERAWG5 | - | EU Grant (GO2.4) | Completed | SC5 Annex I |  | SERAWG-04-14 | submitted to SERAWG4 by the Australian delegation
2021/22 | SER2021-05 | SERAWG | Development of Harvest Strategy -Evaluation of Three Provisional Harvest Strategies (ToR1) | Consultant | MARAM consultants (Brandao, Butterworth, Johnston) | 2021-10-15 | 2021-11-15 | 2021-12-29 | 2022-01-29 | SERAWG4 | 7500 | MoP5; MoP6 (remaining budgeted funds) | Completed | MoP5 para 53 & 132 |  | SERAWG-04-11 | report submitted and reviewed by the Secretariat, still needs PM review
2021/22 | SEC2021-01 | SC/SEC | Harmonisation of Scientific Observer programmes | Intersessional WG | Sebastian | 08-10-2021 | N/A | N/A | 2022-02-05 | SERAWG4; PAEWG4 | - | - | Ongoing | SC6 para 70 |  | Not yet defined | SC Circular 2021-6,7,9 - Presentation to be done at SC7 and SC8- SC Circular 2022 + Rapporteur report
2021/22 | SER2021-04 | SERAWG | ORY Acoustic Stock Assessment | Consultant | R. Ureta | 2021-09-01 | 2021-11-01 | 2021-12-29 | 2022-01-29 | SERAWG4 | 25000 | MoP7 | Ongoing | SC6 Annex G | SER2021-02 | Not yet defined | report under revision and about to be submitted to SERAWG4 (late)
2021/22 | SER2021-05 | SERAWG | Development of Harvest Strategy - Roadmap (ToR2) | Consultant | CT university (Butterworth) | 2021-10-15 | 2021-11-15 | 2021-12-29 | 2022-01-29 | SERAWG4 | 7500 | MoP5; MoP6 (remaining budgeted funds) | Ongoing | MoP5 para 53 & 133 |  | Not yet defined | report under revision and about to be submitted to SERAWG4 (late)
2021/22 | PAE2021-01a | PAEWG | Classification of key biological,geological and oceanographic data (ToR1) | Consultant | Muséum National d’Histoire Naturelle (Leroy, Ramiro-Sanchez) | 04-08-2021 | 13-09-2021 | 2022-01-05 | 2022-04-30 | PAEWG4 | 15000 | MoP8 | Ongoing | SC6 Annex G |  | PAEWG-04-10 | Projects PAE2021abcde are combined into a single overall consultancy dor a TOTAL Cost of 60000€ (15K€ MoP + 45K€ EU Grant). Progress report submitted to PAEWG4
2021/22 | PAE2020-02b | PAEWG | VME mapping (year 2) | Consultant | BOREA Laboratory (Leroy, Ramiro-Sanchez, Martin) | Completed | Completed | 2022-02-05 | 2022-03-01 | PAEWG4 | 96000 | EU Grant (2020-2022); MoP6; MoP7 | Ongoing | MoP5 | PAE2020-02a | PAEWG-04-09 | This consultancy is paid by an EU Grant signed in 2019 and MoP,
2021/22 | SER2021-06 | SERAWG | Alfonsino acoustics feasibility | Consultant |  | To be reviewed | To be decided at SERAWG 4 | 15-01-2022 | 2022-01-29 | SERAWG4 | 5000 | MoP7 | Outstanding | SC6 Annex G |  |  | SERAWG decided to address this through an intersessional workshop
2021/22 | - | SERAWG | Review of CMM 2019/12 (Shark) | SC |  | N/A | N/A | N/A | 2022-01-29 | SERAWG4 | - | - | Outstanding | MoP8 para 53; CC5 para 17 |  |  | Code to be decided and project to be confirmed during the SERAWG4
2021/22 | PAE2021-05 | PAEWG | Review seabird bycatch mitigation (CMM2021/02, 2019/13, ACAP) | SC |  | N/A | N/A | N/A | 2022-02-05 | PAEWG4 | - | - | Outstanding | MoP8 para 114; SC6 para 133 | PAE2021-02 |  | To be considered at PAEWG4
2021/22 | SEC2021-12 | SC/SEC | Annual report of VME encounters | SC |  | N/A | N/A | N/A | 25/02/2022 | SC7 |  |  | Completed | CMM2020/01 para 13 |  |  | No encounters in 2021
2021/22 | PAE2022-01 | PAEWG | Annual review of VME encounters | SC |  | TBD | TBD | TBD | 2023-01-31 | PAEWG5 | - | - | TBD |  |  |  | No encounters in 2021
2021/22 | SEC2021-05 | SC/SEC | Data & information systems | Consultant | Keith Reid (Ross Analytics) | 20-08-2021 | 01-10-2021 | 2022-01-19 | 2022-02-19 | SC7 | 15000 | MoP7 (Reserve fund) | Ongoing | MoP8 para 94-95 |  | Not yet defined | Draft report submitted to SC7 (Secretariat review done)
2021/22 | SEC2021-06 | SC/SEC | Security audit: Physical security | Consultant | Orange Cyberdefense (Reunion) | 20-08-2021 | 01-10-2021 | 2022-01-19 | 2022-02-19 | SC7 | 20000 | MoP7 (Reserve fund) | Ongoing | MoP8 para 94-95; MoP8 Annex O
2021/22 | SEC2021-02 | SC/SEC | SC Chair position | Consultant | Alistair Dunn | N/A | 2021-07-30 | N/A | 2022-06-04 | MoP9 | 37575 | MoP8 Item 9.2 | Ongoing | MoP8 para 122 |  | No report | Contract signed, until MoP 8
2021/22 | PAE2021-03b | PAEWG | VME indicator species thresholds | Intersessional WG/PAEWG4 |  | TBD | N/A | 2022-01-05 | 2022-02-05 | PAEWG4 | - | - | TBD | MoP8 para 100; SC6 para 90 | PAE2021-03a |  | To be organised in intersession and presented to MoP9.
2021/22 | SEC2021-11 | SC/SEC | Development of 3-5 yr. Scientific Committee budget | SC Chairs committee |  | N/A | N/A | 2021-12-29 | 2022-01-29 | SEAWG4; PAEWG4; SC7 | - | - | Ongoing | MoP8 para 194
2021/22 | SEC2021-09 | SC/SEC | Review of CMM [2021/02] Data standards | Secretariat |  | N/A | N/A | N/A | 2022-08-18 | SC7 | - | - | Ongoing | MoP8 para 155 |  |  | No update expected in 2022 at SC7
2021/22 |  | SERAWG | Update BYS maturity staging classification | SC |  | N/A | N/A | 2021-12-31 | 2022-01-30 | SERAWG5 | - | - | Outstanding | SC6 para 107 |  |  | Code to be decided and project to be confirmed during the SERAWG4
2021/22 |  | SERAWG | Review progress under CMM 2019/12 (Sharks) | SC |  | N/A | N/A | 2021-12-31 | 2022-01-30 | SERAWG5 | - | - | Outstanding | SC6 para 131 |  |  | Code to be decided and project to be confirmed during the SERAWG4
2021/22 | SEC2021-04 | SC/SEC | E-monitoring schemes | Intersessional WG |  | TBD | N/A | 2021-12-31 | 2022-01-30 | SERAWG4; PAEWG4 | - | - | TBD | SC6 para 66 |  |  | Will be combined with SEC2021-01
2021/22 | PAE2021-01f ? | PAEWG | Support work on benthic bioregionalization (underway) and (future) investigate possible habitat suitability modelling | Consultant | [5 empty] | PAEWG5 (Final report) |  |  | TBD | SC6 Annex G
2021/22 |  | PAEWG | Review of VME indicator taxa list | SC Delegations |  | N/A | N/A | 2022-01-05 | 2022-02-05 | PAEWG4 | - | - | Outstanding | MoP8 para 99; SC6 para 89 |  |  | Must be planned during the PAEWG4 to be done by the MoP9
2021/22 |  | PAEWG | VME indicator species threshold development plan | Intersessional WG/Consultant |  | N/A | N/A | 2022-01-05 | 2022-02-05 | PAEWG4 | - | - | Outstanding | MoP8 para 100 |  |  | Must be planned during the PAEWG4 to be done by the MoP9
2021/22 |  | PAEWG | VME indicator species threshold | Intersessional WG
2021/22 |  | SC/SEC | VME management | Intersessional WG |  | TBD | N/A | N/A |  | MoP9
2021/22 |  | SC/SEC | Ecosystem summaries and fisheries overview workshop | Intersessional WG |  | TBD | N/A | N/A |  | MoP9
2021/22 |  | SC/SEC | Seabird mitigation options | Intersessional WG |  | TBD | N/A | N/A |  | MoP9
2021/22 |  | SC/SEC | Alfonsino acoustic surveys feasibility | Intersessional WG |  | TBD | N/A | N/A |  | MoP9
2021/22 |  | SC/SEC | Monitoring of alfonsino, toothfish, orange roughy | Intersessional WG |  | TBD | N/A | N/A |  | MoP9
2021/22 |  | PAEWG | Review seabird bycatch mitigation (CMM2021/02, 2019/13, ACAP) | SC Delegations |  | TBD | N/A | N/A |  | MoP9
2021/22 |  | SC/SEC | Biological data collection protocol | Intersessional WG |  | TBD | N/A | N/A |  | MoP9
2021/22 |  | SC/SEC | Acoustic data protocol | Intersessional WG |  | TBD | N/A | N/A |  | MoP9 | [6 empty] | Small WG to develop the protocol subject to decisions by SC7
2021/22 |  | SC/SEC | Harvest strategies (roadmap) | Intersessional WG |  | TBD | N/A | N/A |  | MoP9 | [6 empty] | Tri party WS (scientists, mangers & industry) subject to decisions by SC7
2022/23 | PAE2021-01b | PAEWG | Identification of representative protected areas within SIOFA (ToR2) | Consultant | Muséum National d’Histoire Naturelle (Leroy, Ramiro-Sanchez) | 04-08-2021 | 13-09-2021 | 2023-01-05 | 2023-03-30 | PAEWG4 (Draft report); PAEWG5 (Final report) | 10000 | EU Grant (GO2) | Ongoing | SC6 Annex G |  | Not yet defined | Projects PAE2021abcde are combined into a single overall consultancy. Marco 23/02/2022: progress report submitted to PAEWG4
2022/23 | PAE2021-01c | PAEWG | Investigate and advise on the use of habitat suitability modelling in predicting benthic species diversity and distribution in SIOFA (ToR3) | Consultant | Muséum National d’Histoire Naturelle (Leroy, Ramiro-Sanchez) | 04-08-2021 | 13-09-2021 | 2022-01-05 | 2023-03-30 | PAEWG4 (Draft report); PAEWG5 (Final report) | 10000 | EU Grant (GO2) | Ongoing | SC6 Annex G | PAE2020-01a | Not yet defined | Projects PAE2021abcde are combined into a single overall consultancy. Marco 23/02/2022: progress report submitted to PAEWG4
2022/23 | PAE2021-01d | PAEWG | Holistic framework for assessing and preventing Significant Adverse Impacts (SAIs) on VMEs (ToR4) | Consultant | Muséum National d’Histoire Naturelle (Leroy, Ramiro-Sanchez) | 04-08-2021 | 13-09-2021 | 2023-02-05 | 2023-04-30 | PAEWG4 (Draft report); PAEWG5 (Final report) | 10000 | EU Grant (2021-2023) (GO2) | Ongoing | SC6 Annex G |  |  | Projects PAE2021abcde are combined into a single overall consultancy.
2022/23 | PAE2021-01e | PAEWG | Identify and update existing and potential SAIs within the SIOFA management area (ToR5) | Consultant | Muséum National d’Histoire Naturelle (Leroy, Ramiro-Sanchez) | 04-08-2021 | 13-09-2021 | 2023-02-05 | 2023-04-30 | PAEWG5 (Final report) | 5000 | EU Grant (2021-2023) (GO2) | Ongoing | SC6 Annex G | PAE2020-01d |  | Projects PAE2021abcde are combined into a single overall consultancy.
2022/23 |  | PAEWG | Development of research and monitoring plans for protected areas | TBD |  | TBD | N/A | N/A |  | MoP9
2022/23 |  | PAEWG | Further ERA for benthic species on the Saya de Malha bank | TBD |  | TBD | N/A | N/A |  | MoP10
2022/23 |  | SERAWG | Review toothfish data collection requirements | SC |  | N/A | N/A | N/A | 2023-01-31 | SERAWG5 | - | - | TBD | CMM2021/15 para 31 |  |  | To be agreed during SERAWG4.
2022/23 |  | SERAWG | Development of stock structure ToRs (ORH, BYS, TOT) | Intersessional WG |  | TBD | N/A | 2022-12-31 | 2023-01-31 | SERAWG4 | - | - | TBD | SC6 Annex G; SC6 para 140
2022/23 |  | SERAWG | Orange roughy stock structure | Consultant |  | TBD | TBD | 2022-12-31 | 2023-01-31 | SERAWG5 | 8334 | EU Grant (2021-2023) (GO1.2) | TBD | SC6 Annex G
2022/23 |  | SERAWG | Alfonsino stock structure | Consultant |  | TBD | TBD | 2022-12-31 | 2023-01-31 | SERAWG5 | 8333 | EU Grant (2021-2023) (GO1.2) | TBD | SC6 Annex G
2022/23 |  | SERAWG | Toothfish stock structure | Consultant |  | TBD | TBD | 2022-12-31 | 2023-01-31 | SERAWG5 | 8333 | EU Grant (2021-2023) (GO1.2) | TBD | SC6 Annex G
2022/23 |  | SERAWG | Alfonsino acoustic abundance index | Consultant |  | TBD | TBD | 2022-12-31 | 2023-01-31 | SERAWG5 | 15000 | MoP8 | TBD | SC6 Annex G | SER2021-05 |  | To be confirmed depending on the outcome of Project SER2021-05
2022/23 |  | SERAWG | Alfonsino stock assessment | Consultant |  | TBD | TBD | 2022-12-31 | 2023-01-31 | SERAWG5 | 25000 | EU Grant (2021-2023) (GO1.1) | TBD | SC6 Annex G | SER2021-03; SER2021-05; SER2021-07; BYS growth curve
2022/23 |  | SERAWG | Alfonsino growth curve | CCPs |  | TBD | TBD | 2022-12-31 | 2023-01-31 | SERAWG5
2022/23 |  | SERAWG | Alfonsino age validation (bomb radiometry) | Consultant |  | N/A | N/A | N/A | 2021-12-31 | SERAWG5 | 5000 | EU grant: GO1.3 | Outstanding |  |  |  | Note that only 5 000 euro are currently available from the EU grant under this budget line
2022/23 |  | SERAWG | Standardised data collection protocols for BYS | SC |  | TBD | TBD | 2022-12-31 | 2023-01-31 | SERAWG6 | - | - | Outstanding | SC6 para 106 |  |  | Code to be decided and project to be confirmed during the SERAWG4
2022/23 |  | SERAWG | Toothfish growth curve (+ otolith collection) | CCPs |  | TBD | TBD | 2022-12-31 | 2023-01-31 | SERAWG5 | 2500 | EU Grant (2021-2023) (G01.3) | TBD | SC6 Annex G
2022/23 |  | SERAWG | Toothfish stock structure (molecular analysis) | CCPs/Consultant |  | N/A | N/A | 2022-12-31 | 2023-01-30 | SERAWG5 | 8300 | EU grant: GO1.2 | Outstanding |  |  |  | (1) SIOFA(Del Cano) and CCAMLR (Crozet, Kerguelen & Prince Edward) (2) SIOFA (William’s Ridge)+CCAMLR(Kerguelen’s and Heard & McDonald's) (EU, France Territories, Japan & Australia) (Japan's cooperation is subject to the tissue sampling protocol) (3) Consultant (8.3K) (EU grant: GO1.2)
2022/23 |  | SERAWG | Monaco Exploration (Saya de Malha Bank） | Monaco foundation | [12 empty] | Subject to decisions made by MoP
2022/23 |  | PAEWG | Review of VME indicator taxa list | SC Delegations |  | TBD | TBD | TBD | 2023-01-30 | PAEWG5 | - | - | Outstanding | MoP8 para 99; SC6 para 89 |  |  | Must be planned during the PAEWG4 to be done by the MoP9
2022/23 |  | PAEWG | Annual review of VME encounters | SC |  | TBD | TBD | TBD | 2023-01-31 | PAEWG5 | - | - | TBD | CMM2020/01 para 16
2022/23 |  | SERAWG | Teleosts ERA update | AUS/CCPs |  | N/A | N/A | N/A | N/A | SERAWG5?
2022/23 |  | SC/SEC | Summary of SIOFA data | Secretariat |  | N/A | N/A | N/A | 25/02/2023 | SC8 |  |  | TBD | CMM2020/01 para 13 |  |  | Secretariat will summarize the available data at SIOFA
2022/23 |  | SC/SEC | Fisheries overview | Secretariat |  | N/A | N/A | N/A | 25/02/2023 | SC8 |  |  | TBD | CMM2020/01 para 13 |  |  | Secretariat will report on relevant SIOFA fisheries (oilfish, toothfish, alfonsino, roughy, tarakihi, 2 wreckfishes)
2022/23 |  | SC/SEC | Ecosystem summary | Secretariat |  | N/A | N/A | N/A | 25/02/2023 | SC8 |  |  | TBD | CMM2020/01 para 13 |  |  | Secretariat will report on ecosystem status
2022/23 |  | SC/SEC | Annual report of VME encounters | Secretariat |  | N/A | N/A | N/A | 25/02/2023 | SC8 |  |  | TBD | CMM2020/01 para 13 |  |  | Secretariat will report if any VME encounters have been submitted by CCPs
2022/23 |  | SC/SEC | Fisheries footprint (including coherence with CCPs footprints) | Secretariat |  | N/A | N/A | N/A | 25/02/2023 | SC8 |  |  | TBD | CMM2020/01 para 13
2022/23 |  | SC/SEC | SIOFA data transformation strategy | Secretariat |  | N/A | N/A | N/A | 25/02/2023 | SC8 |  |  | TBD |  |  |  | Pending SC7 recommendations
2022/23 |  | SC/SEC | Develop Data Base system and analyses | Consultant |  | TBD | TBD | TBD | 2023-01-31 | SC8 | 20000 | EU Grant (2021-2023) (GO4) | TBD | EUG 2020 GO4 | SEC2021-05 and SEC2021-06 |  | Must to be planned in 2022-2023 considering the outcome of the SEC2021-05 and SEC2021-06
Note on D51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: bycatch mitigation measures? advice?

## Glossary of terms-colors
Color | Project Status | Lead | Provider
| Completed | SC/SEC | Consultant
| Ongoing | PAEWG | Secretariat
| Outstanding | SERAWG | SC Chairs committee
no fill | TBD |  | SC
SC Delegations
Intersessional WG
???
Blue text | Recurring activities |  | TBD